## Blad1
Project week number
Activities | Sub-activities | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18 | 19 | 20
Reporting | Plan of Approach | bar: Project week number 1 to Project week number 2
SRD | bar: Project week number 3
SDD | bar: Project week number 4 to Project week number 6
MDD | bar: Project week number 7 to Project week number 18
Mid-term presentation | bar: Project week number 10
Final presentation | bar: Project week number 18 to Project week number 19
Researching | Researching | bar: Project week number 3 to Project week number 4
Design hardware | Design first iteration | bar: Project week number 5 to Project week number 7
Design second iteration | bar: Project week number 8 to Project week number 10
Design third iteration | bar: Project week number 11 to Project week number 13
Design fourth iteration | bar: Project week number 14 to Project week number 16
Design firmware | Control battery emulator | bar: Project week number 8 to Project week number 10
Control communication between the modules | bar: Project week number 8 to Project week number 10
Realization | Create PCB | bar: Project week number 7; Project week number 10; Project week number 13; Project week number 16
Program PCB | bar: Project week number 7; Project week number 10; Project week number 13; Project week number 16
Verification | Verify first iteration | bar: Project week number 8
Verify second iteration | bar: Project week number 11
Verify third iteration | bar: Project week number 14
Verify fourth iteration | bar: Project week number 17